## 2020 Marketing Calendar
Treefrog 2020 Marketing Calendar | 2020
Development | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
Delivery | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 11 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
Overall Marketing Strategy
Budgeting and Cadence Strategy | bar: January 6; April 6; July 6; October 5
Integrated Marketing Strategy | bar: January 6
Digital Marketing Strategy | bar: January 6; July 6
Communications Planning | bar: January 6; July 6
Measurment
Performance Indicator Strategy | bar: January 20
Reporting Tools Analysis/Setup | bar: January 20
Dashboard Setup | bar: January 20
Tool Testing | bar: January 20
Brand Strategy
Brand Positioning | bar: January 20 to January 27
Brand Persona Development | bar: January 27 to February 3
Moodboard Development | bar: February 3 to February 10
Corporate Renaming | bar: February 17 to February 24
Tagline Development | bar: March 2
Logo Development/Maturation | bar: March 2 to March 9
Corporate Photography (People/Space) | bar: March 2 to March 9
Brand Standards Guide | bar: March 2 to March 9
Social Brand Collateral | bar: March 9 to March 16
Corporate Brand Collateral | bar: March 9 to March 16
Marketing Print Collateral
Business Cards | bar: March 16 to March 23
Letterhead | bar: March 16 to March 23
PPT Template | bar: March 16 to March 23
Product Sheets | bar: March 16 to March 23
Web Strategy
Website Review | bar: March 2
Content Audit | bar: March 2
Data Analysis (a.k.a. Reporting) | bar: March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Technical Audit | bar: March 30; June 29; September 28; December 28
Security Review & Updates | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 9; December 7
New Website Build (or Refresh)
Site Architecture & User Pathing | bar: March 9 to March 16
Graphic Design/Template Selection | bar: March 23 to March 30
HTML Programming | bar: March 23 to April 6
CMS/Platform Selection/Installation | bar: April 6
Keyword Assessment | bar: April 6 to April 13
Content Development | bar: April 13 to April 27
Content Coordination | bar: April 13 to April 27
Content Insertion & Set Up | bar: April 27 to May 4
Browser & UX Testing | bar: May 11
Go Live | bar: May 18
Set up of new Architecture/Pathing | bar: May 18
Set up of Google Analytics | bar: May 18
Set up Google Tag Manager | bar: May 18
Set up Google Console | bar: May 18
Link Social to website | bar: May 18
Search Engine Optimization (Initial) | bar: May 18
Extended Website Integrations
Email Marketing Integration | bar: June 8
CRM Selection and Adoption | bar: June 8
CRM Integration | bar: June 8 to June 15
ERP Integration | bar: June 15
POS Integration | bar: June 15
Call Tracking | bar: June 15
Live Chat & Chatbots | bar: June 15
Marketing Automation
Platform Analysis | bar: July 13
Website Integration | bar: July 13
Scripting and Content Development | bar: July 13 to July 20
Automation Development | bar: July 20
Setup and GoLive | bar: July 20
Ongoing Web Activities
Keyword Strategy | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Keyword Research | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Keyword Reporting | bar: January 13; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Search Engine Audit | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Search Engine Optimization (Technical) | bar: January 13; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Search Engine Optimization (On-Page) | bar: January 20; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Search Engine Optimization (Linkbuilding) | bar: January 20; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
External Search Advertising (PAID)
Paid Search Strategy | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Competitor Analysis | bar: January 6 to January 20
Google Search Ads
Google Display Ads
Google Remarketing Ads
Google Shopping Ads
Google Local Search Ads
Programatic
YouTube: In-Stream
YouTube: In-Discovery
YouTube: In-Search
Content Marketing
Content Marketing Strategy
Content Calendar | bar: January 6; April 6; July 6; October 5
Blog Post Writing | bar: January 13; February 10; March 9; April 13; May 11; June 8; July 13; August 11; September 14; October 12; November 9; December 7
Vlog Strategy | bar: January 6; April 6; July 6; October 5
Podcast Strategy | bar: January 6; April 6; July 6; October 5
Email Marketing
Email Marketing Strategy | bar: January 6; April 6; July 6; October 5
Email Newsletter Design and Setup | bar: January 6
Article Development/Posting | bar: January 20; February 17; March 16; April 20; May 18; June 15; July 20; August 17; September 21; October 19; November 16; December 14
Distribution List Building/Purchasing | bar: January 20; February 17; March 16; April 20; May 18; June 15; July 20; August 17; September 21; October 19; November 16; December 14
Email Development Draft & Design (monthly) | bar: January 20; February 17; March 16; April 20; May 18; June 15; July 20; August 17; September 21; October 19; November 16; December 14
Deployment | bar: January 20; February 17; March 16; April 20; May 18; June 15; July 20; August 17; September 21; October 19; November 16; December 14
Evergreen Content
Keyword Assesment | bar: February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Content Topic List | bar: January 13; February 10; March 9; April 13; May 11; June 8; July 13; August 11; September 14; October 12; November 9; December 7
Article Development and Post | bar: January 20; February 17; March 16; April 20; May 18; June 15; July 20; August 17; September 21; October 19; November 16; December 14
Promotion Strategy | bar: February 24; March 23; April 27; May 25; June 22; July 27; August 24; September 28; October 26; November 23; December 21
Case Studies
Research and Interview | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Case Study Development and Post | bar: January 13; February 10; March 9; April 13; May 11; June 8; July 13; August 11; September 14; October 12; November 9; December 7
Promotion Strategy | bar: January 6; April 6; July 6; October 5
Thought Leadership Content
Keyword Research (SEO) | bar: January 6
Content Topic List | bar: January 13
Article Development and Post | bar: February 3; March 2; March 30; April 27; May 25; June 22; July 20; August 17; September 14; October 12; November 9; December 7
Mascot Content Development
Promotion Strategy | bar: January 6; April 6; July 6; October 5
Video/Explainer Content
Storytelling Strategy | bar: January 6; April 6; July 6; October 5
Scripring | bar: January 6; April 6; July 6; October 5
StoryBoards | bar: January 6; April 6; July 6; October 5
Video Development, editing and animation | bar: January 6; April 6; July 6; October 5
Promotion Strategy | bar: January 6; April 6; July 6; October 5
Social Media
Social Media Strategy
Social Content Calendar | bar: January 6; February 3; March 2; April 6; May 4; June 1; July 6; August 3; September 7; October 5; November 2; November 30
Social Guidelines/Policy
Social Branding
Team Training | bar: January 6
Organic and Paid Managment
Twitter
LinkedIn
Facebook
Instagram
TikTok
YouTube
Alternative Watering Holes
Influencer Marketing
influencer Strategy | bar: January 6
Influencer Relations Development
Influencer Content Creation
Influencer Campaign Engagment and Managment
Direct Mail
Campaign Strategy
Design and Print
Send Cadence
Follow Cadence
Web Integration (Personal URLs)
Event/Trade Show/Conference Planning
Attend Events | bar: May 18 to May 25
Booth/Pull-ups/Display | bar: April 20 to May 4
Print Collateral | bar: April 20 to May 4
Video/Support Material | bar: April 20 to May 4
Social Promotion Calender | bar: May 4 to June 15
Monitor and Engage | bar: March 9; March 23; April 6; April 20; May 4 to June 15
Tradeshow Email Drip Campaign | bar: May 11 to July 6; July 20; August 3; August 24; September 14; October 12; November 9; December 7
Publications
Communications Strategy/Budget
Publisher Negotiation/Management
Copywriting
Advertisement/Layout Design
Web Integration (General URLs)
Dynamic QR Codes
Media Buying
Radio
Television
Out-of-Home (Billboards, Backlits, Street Signs)
Transit (Buses, Trains and Terminals)
English /French required
Print (Newspapers, Magazines,Trade Publications)
Digital (Pre-roll, Online Commercials)
Premiums and Incentives
Apparel or other branded items
"Trinkets and Trash"
Public Relations
Environmental Policy Establishment/Communication | bar: January 6
Charitable Affiliations and Programs | bar: January 6
Social Responsiblity Policies/Communication | bar: January 6
Press Release Strategy
Story ideation
Story pitching
Awards Sponsorship/Application | bar: January 6; April 6; July 6; October 5
Awards Attendance | bar: February 17; October 26; November 16
Reputation Management
Online Review Management | bar: January 6; April 6; July 6; October 5
Crisis Communication Strategy | bar: January 6
Sales Pitch Deck
Content Creation | bar: January 6 to January 20
Theme/Design | bar: January 13
Messaging and multimedia content | bar: January 27; February 24; March 30